## Slide 1: Chapter 6: Project Time Management
Information Technology Project Management, Seventh Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives
Understand the importance of project schedules and good project time management
Discuss the process of planning schedule management
Define activities as the basis for developing project schedules
Describe how project managers use network diagrams and dependencies to assist in activity sequencing
Understand the relationship between estimating resources and project schedules
Explain how various tools and techniques help project managers perform activity duration estimates

## Slide 3: Learning Objectives
Use a Gantt chart for planning and tracking schedule information, find the critical path for a project, and describe how critical chain scheduling and the Program Evaluation and Review Technique (PERT) affect schedule development
Discuss how reality checks and discipline are involved in controlling and managing changes to the project schedule
Describe how project management software can assist in project time management and review words of caution before using this software

## Slide 4: Importance of Project Schedules
Managers often cite delivering projects on time as one of their biggest challenges
Time has the least amount of flexibility; it passes no matter what happens on a project
Schedule issues are the main reason for conflicts on projects, especially during the second half of projects

## Slide 5: Individual Work Styles and Cultural Differences Cause Schedule Conflicts
One dimension of the Meyers-Briggs Type Indicator focuses on peoples’ attitudes toward structure and deadline
Some people prefer to follow schedules and meet deadlines while others do not (J vs. P)
Difference cultures and even entire countries have different attitudes about schedules

## Slide 6
迈尔斯布里格斯类型指标(MBTI)表征人的性格，是由美国的凯恩琳·布里格斯和她的女儿伊莎贝尔·布里格斯·迈尔斯制定的。该指标以瑞士心理学家荣格划分的8种类型为基础，加以扩展，形成四个维度，每个点对应每个人的性格。
  ① 外倾(E)－内倾(I)
  ② 感觉(S)－直觉(N)
  ③ 思维(T)－情感(F)
  ④ 判断(J)－知觉(P)

## Slide 7
外倾－内倾
外倾型 内倾型
与他人相处精力充沛 独自度过时光精力充沛 行动
之后思考 思考， 之后行动 喜欢边想边说出声
在心中思考问题 易于“读”和了解；随意地分享个人情况 更封闭，更愿意在经挑选的小群体中分享个人的情况
说的多于听的 听的比说的多
高度热情地社交 不把兴奋说出来
反应快，喜欢快节奏 仔细考虑后，才有所反应
重于广度而不是深度 喜欢深度而不是广度

## Slide 8
感觉－直觉
感觉型 直觉型
相信确定和有型的东西 相信灵感和推断
喜欢新想法—除非它们有实际意义 为了自己的利益，喜欢新思想和概念
重视现实性和常情 重视想象力和独创力
喜欢使用和琢磨已知的技能 喜欢学习新技能，但掌握之后很容易就厌倦了
留心具体的和特殊的； 进行细节描述
留心普遍的和有象征性的； 使用隐喻和类比
循序渐进地讲述有关情况 跳跃性地展现事实
着眼于现实 以一种绕圈子的方式着眼于未来

## Slide 9
思维－情感
思维型 情感型
退后一步思考，对问题进行非个人因素的分析 超前思考，考虑行为对他人的影响
重视符合逻辑、公正、公平的价值； 一视同仁 重视同情与和睦：重视准则的例外性
被认为冷酷、麻木、漠不关心 被认为感情过多，缺少逻辑性，软弱
认为圆通比坦率更重要 认为圆通与坦率同样重要
只有情感符合逻辑时，才认为它可取 无论是否有意义，认为任何感情都可取
被渴望成就而激励 被为了获得欣赏而激励
很自然地看到缺点，倾向于批评

## Slide 10
判断－知觉
判断型 知觉型
做了决定后最为高兴 当各种选择都存在时，感到高兴
有“工作原则”：工作第一，玩其次（如果有时间的话） “玩的原则”：现在享受，然后再完成工作
建立目标，准时地完成 随着新信息的获取，不断改变目标
愿意知道它们将面对的情况 喜欢适应新情况 着重结果（重点在于完成任务）
着重过程（重点在于如何完成工作） 满足感来源于完成计划 满足感来源于计划的开始
把时间看作有限的资源，认真地对待最后期限
认为时间是可更新的资源，而最后期限也是有收缩的

## Slide 11: 所属类型
内倾感觉思维判断（ISTJ） 内倾感觉情感判断（ISFJ）
内倾直觉情感判断（INFJ） 内倾直觉思维判断（INTJ）
内倾感觉思维知觉（ISTP） 内倾感觉情感知觉（ISFP）
内倾直觉情感知觉（INFP） 内倾直觉思维知觉（INTP）
外倾感觉思维判断（ESTJ） 外倾感觉情感判断（ESFJ
外倾直觉情感判断（ENFJ） 外倾直觉思维判断（ENTJ）
外倾感觉思维知觉（ESTP） 外倾感觉情感知觉（ESFP）
外倾直觉情感知觉（ENFP） 外倾直觉思维知觉（ENTP）

## Slide 12: Media Snapshot
In contrast to the 2002 Salt Lake City Winter Olympic Games (see Chapter 4’s Media Snapshot), planning and scheduling was very different for the 2004 Summer Olympic Games held in Athens, Greece
Many articles were written before the opening ceremonies predicting that the facilities would not be ready in time. …many people were pleasantly surprised by the amazing opening ceremonies, beautiful new buildings, and state-of-the-art security and transportation systems in Athens
The Greeks even made fun of critics by having construction workers pretend to still be working as the ceremonies began

## Slide 13: Project Time Management Processes
Planning schedule management: determining the policies, procedures, and documentation that will be used for planning, executing, and controlling the project schedule
Defining activities: identifying the specific activities that the project team members and stakeholders must perform to produce the project deliverables
Sequencing activities: identifying and documenting the relationships between project activities
Estimating activity resources: estimating how many resources a project team should use to perform project activities
Estimating activity durations: estimating the number of work periods that are needed to complete individual activities
Developing the schedule: analyzing activity sequences, activity resource estimates, and activity duration estimates to create the project schedule
Controlling the schedule: controlling and managing changes to the project schedule

## Slide 14: Figure 6-1. Project Time Management Summary

## Slide 15: Planning Schedule Management
The project team uses expert judgment, analytical techniques, and meetings to develop the schedule management plan
A schedule management plan includes:
  Project schedule model development
  The scheduling methodology
  Level of accuracy and units of measure
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 16: Defining Activities
An activity or task is an element of work normally found on the work breakdown structure (WBS) that has an expected duration, a cost, and resource requirements
Activity definition involves developing a more detailed WBS and supporting explanations to understand all the work to be done so you can develop realistic cost and duration estimates

## Slide 17: Activity Lists and Attributes
An activity list is a tabulation of activities to be included on a project schedule that includes
  the activity name
  an activity identifier or number
  a brief description of the activity
Activity attributes provide more information such as predecessors, successors, logical relationships, leads and lags, resource requirements, constraints, imposed dates, and assumptions related to the activity

## Slide 18: Milestones
A milestone is a significant event that normally has no duration
It often takes several activities and a lot of work to complete a milestone
They’re useful tools for setting schedule goals and monitoring progress
Examples include obtaining customer sign-off on key documents or completion of specific products

## Slide 19: What Went Wrong?
At the U.S. Federal Bureau of Investigation (FBI), poor time management was one of the reasons behind the failure of Trilogy, a “disastrous, unbelievably expensive piece of vaporware, which was more than four years in the (un)making. The system was supposed to enable FBI agents to integrate intelligence from isolated information silos within the Bureau.”*
In May 2006, the Government Accounting Agency said that the Trilogy project failed at its core mission of improving the FBI’s investigative abilities and was plagued with missed milestones and escalating costs. Sentinel replaced Trilogy in 2007.
During a test exercise in 2011, Sentinel experienced two outages, and the FBI determined that the current hardware structure was inadequate. Unfortunately, history seemed to repeat itself as troubles still loomed with Sentinel in 2012
*Roberts, Paul, “Frustrated contractor sentenced for hacking FBI to speed deployment,”
InfoWorld Tech Watch, (July 6, 2006).

## Slide 20: Sequencing Activities
Involves reviewing activities and determining dependencies
A dependency or relationship is the sequencing of project activities or tasks
You must determine dependencies in order to use critical path analysis

## Slide 21: Three types of Dependencies
Mandatory dependencies: inherent in the nature of the work being performed on a project, sometimes referred to as hard logic
Discretionary dependencies: defined by the project team., sometimes referred to as soft logic and should be used with care since they may limit later scheduling options
External dependencies: involve relationships between project and non-project activities

## Slide 22: Network Diagrams
Network diagrams are the preferred technique for showing activity sequencing
A network diagram is a schematic display of the logical relationships among, or sequencing of, project activities
Two main formats are the arrow and precedence diagramming methods

## Slide 23: Figure 6-2. Network Diagram for Project X

## Slide 24: Arrow Diagramming Method (ADM)
Also called activity-on-arrow (AOA) network diagrams
Activities are represented by arrows
Nodes or circles are the starting and ending points of activities
Can only show finish-to-start dependencies

## Slide 25: Process for Creating AOA Diagrams
1. Find all of the activities that start at node 1. Draw their finish nodes and draw arrows between node 1 and those finish nodes. Put the activity letter or name and duration estimate on the associated arrow
2. Continuing drawing the network diagram, working from left to right. Look for bursts and merges. Bursts occur when a single node is followed by two or more activities. A merge occurs when two or more nodes precede a single node
3. Continue drawing the project network diagram until all activities are included on the diagram that have dependencies
4. As a rule of thumb, all arrowheads should face toward the right, and no arrows should cross on an AOA network diagram

## Slide 26: Precedence Diagramming Method (PDM)
Activities are represented by boxes
Arrows show relationships between activities
More popular than ADM method and used by project management software
Better at showing different types of dependencies

## Slide 27: Figure 6-3. Task Dependency Types

## Slide 28: Figure 6-4. Sample PDM Network Diagram

## Slide 29: Estimating Activity Resources
Before estimating activity durations, you must have a good idea of the quantity and type of resources that will be assigned to each activity; resources are people, equipment, and materials
Consider important issues in estimating resources
  How difficult will it be to do specific activities on this project?
  What is the organization’s history in doing similar activities?
  Are the required resources available?
A resource breakdown structure is a hierarchical structure that identifies the project’s resources by category and type

## Slide 30: Activity Duration Estimating
Duration includes the actual amount of time worked on an activity plus elapsed time
Effort is the number of workdays or work hours required to complete a task
Effort does not normally equal duration
People doing the work should help create estimates, and an expert should review them

## Slide 31: Three-Point Estimates
Instead of providing activity estimates as a discrete number, such as four weeks, it’s often helpful to create a three-point estimate
  an estimate that includes an optimistic, most likely, and pessimistic estimate, such as three weeks for the optimistic, four weeks for the most likely, and five weeks for the pessimistic estimate
Three-point estimates are needed for PERT and Monte Carlo simulations

## Slide 32: Developing the Schedule
Uses results of the other time management processes to determine the start and end date of the project
Ultimate goal is to create a realistic project schedule that provides a basis for monitoring project progress for the time dimension of the project
Important tools and techniques include Gantt charts, critical path analysis, and critical chain scheduling, and PERT analysis

## Slide 33
PEST分析是指宏观环境的分析，宏观环境又称一般环境，是指影响一切行业和企业的各种宏观力量。对宏观环境因素作分析，不同行业和企业根据自身特点和经营需要，分析的具体内容会有差异，但一般都应对政治（Political）、经济（Economic）、技术（Technological）和社会（Social）这四大类影响企业的主要外部环境因素进行分析。简单而言，称之为PEST分析法。

## Slide 34: Gantt Charts
Gantt charts provide a standard format for displaying project schedule information by listing project activities and their corresponding start and finish dates in a calendar format
Symbols include:
  A black diamond: a milestones
  Thick black bars: summary tasks
  Lighter horizontal bars: durations of tasks
  Arrows: dependencies between tasks

## Slide 35: Figure 6-5. Gantt Chart for Project X

## Slide 36: Figure 6-6. Gantt Chart for Software Launch Project

## Slide 37: Adding Milestones to Gantt Charts
Many people like to focus on meeting milestones, especially for large projects
Milestones emphasize important events or accomplishments on projects
Normally create milestone by entering tasks with a zero duration, or you can mark any task as a milestone

## Slide 38: SMART Criteria
Milestones should be
  Specific
  Measurable
  Assignable
  Realistic
  Time-framed

## Slide 39: Best Practice
Schedule risk is inherent in the development of complex systems. Luc Richard, the founder of www.projectmangler.com, suggests that project managers can reduce schedule risk through project milestones, a best practice that involves identifying and tracking significant points or achievements in the project. The five key points of using project milestones include the following:
  1. Define milestones early in the project and include them in the Gantt chart to provide a visual guide
  2. Keep milestones small and frequent
  3. The set of milestones must be all-encompassing
  4. Each milestone must be binary, meaning it is either complete or incomplete.
  5. Carefully monitor the critical path

## Slide 40: Figure 6-7. Sample Tracking Gantt Chart

## Slide 41: Critical Path Method (CPM)
CPM is a network diagramming technique used to predict total project duration
A critical path for a project is the series of activities that determines the earliest time by which the project can be completed
The critical path is the longest path through the network diagram and has the least amount of slack or float
Slack or float is the amount of time an activity may be delayed without delaying a succeeding activity or the project finish date

## Slide 42: Calculating the Critical Path
First develop a good network diagram
Add the duration estimates for all activities on each path through the network diagram
The longest path is the critical path
If one or more of the activities on the critical path takes longer than planned, the whole project schedule will slip unless the project manager takes corrective action

## Slide 43: Figure 6-8. Determining the Critical Path for Project X

## Slide 44: More on the Critical Path
A project team at Apple computer put a stuffed gorilla on the top of the cubicle of the person currently managing critical task
The critical path is not the one with all the critical activities; it only accounts for time
  Remember the example of growing grass being on the critical path for Disney’s Animal Kingdom
There can be more than one critical path if the lengths of two or more paths are the same
The critical path can change as the project progresses

## Slide 45: Using Critical Path Analysis to Make Schedule Trade-offs
Free slack or free float is the amount of time an activity can be delayed without delaying the early start of any immediately following activities
Total slack or total float is the amount of time an activity may be delayed from its early start without delaying the planned project finish date
A forward pass through the network diagram determines the early start and finish dates
A backward pass determines the late start and finish dates

## Slide 46: Figure 6-9. Calculating Early and Late Start and Finish Dates

## Slide 47: Table 6-1. Free and Total Float or Slack for Project X

## Slide 48: Using the Critical Path to Shorten a Project Schedule
Three main techniques for shortening schedules
  Shortening durations of critical activities/tasks by adding more resources or changing their scope
  Crashing activities by obtaining the greatest amount of schedule compression for the least incremental cost
  Fast tracking activities by doing them in parallel or overlapping them

## Slide 49: Importance of Updating Critical Path Data
It is important to update project schedule information to meet time goals for a project
The critical path may change as you enter actual start and finish dates
If you know the project completion date will slip, negotiate with the project sponsor

## Slide 50: Critical Chain Scheduling
Critical chain scheduling
  a method of scheduling that considers limited resources when creating a project schedule and includes buffers to protect the project completion date
Uses the Theory of Constraints (TOC)
  a management philosophy developed by Eliyahu M. Goldratt and introduced in his book The Goal.
Attempts to minimize multitasking
  when a resource works on more than one task at a time

## Slide 51: Figures 6-10.a and b. Multitasking Example

## Slide 52: Buffers and Critical Chain
A buffer is additional time to complete a task
Murphy’s Law states that if something can go wrong, it will
Parkinson’s Law states that work expands to fill the time allowed
In traditional estimates, people often add a buffer to each task and use it if it’s needed or not
Critical chain scheduling removes buffers from individual tasks and instead creates
  a project buffer or additional time added before the project’s due date
  feeding buffers or additional time added before tasks on the critical path

## Slide 53: 帕金森定律
帕金森定律表明：只要还有时间，工作就会不断扩展，直到用完所有的时间。换一种说法是：工作总是会拖到最后一刻才会被完成。在行政管理中，行政机构会像金字塔一样不断增多，行政人员会不断膨胀，每个人都很忙，但组织效率越来越低下。
举例：当官的A君感到工作很累很忙时，一定要找比他级别和能力都低的C先生和D先生当他的助手，把自己的工作分成两份分给C、D，自己掌握全面。C和D还要互相制约，不能和自己竞争。当C工作也累也忙时，A就要考虑给C配二名助手；为了平衡，也要给D配两名助手，于是一个人的工作就变成七个人干，A君的地位也随之抬高。

## Slide 54
帕金森定律必须同时满足下面四个条件：
第一：必须要有一个组织，这个组织必须有其内部运作的活动方式，其中管理要在这个组织中占有一定的地位。
第二：寻找助手以达到自己目的的不称职的管理者本身不具有对权力的垄断性。
第三：这个管理者能力极其平庸，他在组织中的角色扮演不称职。
第四：这个组织一定是一个不断自我要求完善的组织，能够不断地吸收新人来补充管理队伍。

## Slide 55: Figure 6-11. Example of Critical Chain Scheduling

## Slide 56: Program Evaluation and Review Technique (PERT)
PERT is a network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates
PERT uses probabilistic time estimates
  duration estimates based on using optimistic, most likely, and pessimistic estimates of activity durations, or a three-point estimate

## Slide 57: PERT Formula and Example
PERT weighted average =
optimistic time + 4X most likely time + pessimistic time
6
Example:
PERT weighted average =
8 workdays + 4 X 10 workdays + 24 workdays = 12 days 6
where optimistic time= 8 days
most likely time = 10 days, and
pessimistic time = 24 days
Therefore, you’d use 12 days on the network diagram instead of 10 when using PERT for the above example

## Slide 58: Schedule Control Suggestions
Perform reality checks on schedules
Allow for contingencies
Don’t plan for everyone to work at 100% capacity all the time
Hold progress meetings with stakeholders and be clear and honest in communicating schedule issues

## Slide 59: Controlling the Schedule
Goals are to know the status of the schedule, influence factors that cause schedule changes, determine that the schedule has changed, and manage changes when they occur
Tools and techniques include
  Progress reports
  A schedule change control system
  Project management software, including schedule comparison charts like the tracking Gantt chart
  Variance analysis, such as analyzing float or slack
  Performance management, such as earned value (chapter 7)

## Slide 60: Reality Checks on Scheduling
First review the draft schedule or estimated completion date in the project charter
Prepare a more detailed schedule with the project team
Make sure the schedule is realistic and followed
Alert top management well in advance if there are schedule problems

## Slide 61: Working with People Issues
Strong leadership helps projects succeed more than good PERT charts
Project managers should use
  empowerment
  incentives
  discipline
  negotiation

## Slide 62: Global Issues
Mittal Steel Poland earned Poland’s Project Excellence Award in 2007 for implementing a SAP system
Derek Prior, research director at AMR Research, identified three things the most successful SAP implementation projects do to deliver business benefits:
  Form a global competence centre
  Identify super-users for each location
  Provide ongoing involvement of managers in business processes so they feel they own these processes

## Slide 63: Using Software to Assist in Time Management
Software for facilitating communications helps people exchange schedule-related information
Decision support models help analyze trade-offs that can be made
Project management software can help in various time management areas

## Slide 64: What Went Right?
Microsoft lists dozens of examples of how customers benefit from using Project 2010. One such customer, Amdocs, a global provider of customer experience systems (CES) software, wanted to help its IT project teams work more efficiently
Employees now have Web-based access from any location, managers have better project visibility, and the company can extend the centralized solution to include more users and applications. Amdocs can now deploy Project Server 2010 in less than a day, or 50 percent faster. Only one person is needed to manage the shared infrastructure.

## Slide 65: Words of Caution on Using Project Management Software
Many people misuse project management software because they don’t understand important concepts and have not had training
You must enter dependencies to have dates adjust automatically and to determine the critical path
You must enter actual schedule information to compare planned and actual progress

## Slide 66: Chapter Summary
Project time management is often cited as the main source of conflict on projects, and most IT projects exceed time estimates
Main processes include
  Plan schedule management
  Define activities
  Sequence activities
  Estimate activity resources
  Estimate activity durations
  Develop schedule
  Control schedule